## Slide 1
IKHT · BINT24 · WORKING GROUP G4
Global Scrum
Team G4
Intercultural collaboration under time pressure
Eight people · four countries · one fixed launch date
Fully remote · no shared team history
Main risk: implicit coordination, not diversity itself
Luca Doerner · Anton Reinicke · Janek Thor Becker
LUCA · 0:40
Notes: Our case follows Global Scrum Team G4, a fictional team developing a mobile fitness app. Eight colleagues in Germany, the United States, India and Japan must deliver within eight months, although they have never worked together or met in person. We examine how team composition, communication and leadership affect delivery. Our central argument is that diversity is not the problem by itself. The real risk is an operating model based on implicit agreement, unclear decision rights and live meetings that cannot include everyone. The case covers formation and the first two sprints; later results are forecasts, not observed facts. Handover: Anton now gives a short overview of the project conditions.

## Slide 2
02
Use Case Overview
ANTON · 0:50
Source: G4 case data and project assumptions
2
PRODUCT
A mobile fitness app built in three connected blocks
01
Tracking
workouts + progress
02
Wearables
sensors + health data
03
Social
profiles + privacy
DELIVERY FRAME
JUN 2026
Start
SPRINT 2
M1 delayed
11 SPRINTS
3 weeks each
FEB 2027
Fixed launch
FIXED DATE
FLEXIBLE SCOPE
STRICT DoD
NO ALL-HANDS OVERLAP
Quality is not flexible
Tests · peer review · English documentation · no critical defects
Notes: The product combines workout tracking, progress statistics, wearable integration and social functions. These features create dependencies around sensors, privacy and international user expectations. The team has about eleven three-week sprints. The launch date is fixed, so the Product Owner may reduce scope through MoSCoW prioritisation. Quality is not flexible: every increment needs tests, peer review, English documentation and no critical defects. Geography is a structural constraint. The US working day starts five hours after the Japanese day ends, so no normal all-hands slot exists. Handover: Janek will show why the team's composition both helps and intensifies this situation.

## Slide 3
03
Team Composition and Development
JANEK · 1:00
Sources: Belbin (2010); Tuckman (1965); G4 case profiles
3
1
GERMANY
PO · Dev5
product + implementation
2
USA
SM · Dev6
process + exploration
3
INDIA
Dev1 · Dev3
sensor + privacy specialists
4
JAPAN
Dev2 · Dev4
full-stack implementation
BELBIN ROLE BALANCE
Strong execution
Many Implementers
and Completer Finishers
Missing
Plant
Monitor Evaluator
TUCKMAN DEVELOPMENT
1
FORMING
2
STORMING
3
NORMING
4
PERFORMING
DIVERSITY PROFILE
42 years
age range
Education · DISC · experience
Models describe patterns, not people.
Notes: Formal leadership is divided between a German Product Owner and a US Scrum Master. Six full-stack developers add flexibility, while Dev1 and Dev3 hold specialist knowledge in sensors, architecture and privacy. The team also spans 42 years of age, different educational experiences and different DISC preferences. Most profiles lean toward Steadiness or Conscientiousness, which supports reliable work but can delay disagreement. Belbin reveals a similar pattern: the team has several Implementers and Completer Finishers, but no Plant for generating alternatives and no Monitor Evaluator for independent review. Tuckman's model places Sprint 0 in forming and the architecture conflict in early storming. Norming and performing are goals, not achieved stages. These models describe possible team patterns; they do not define any individual. Handover: Luca now connects those patterns to the team's communication failure.

## Slide 4
04
Communication Styles: Hofstede and Hall
LUCA · 1:10
Sources: Hall (1976); Hofstede et al. (2010); Minkov & Kaasa (2021)
4
“
Why was the integration not completed?
LOW-CONTEXT READING
A precise request for facts
Meaning sits mainly in the words.
HIGH-CONTEXT READING
Public blame and loss of face
Audience, hierarchy and tone carry meaning.
HOFSTEDE AS TESTABLE HYPOTHESES
POWER DISTANCE · speaking up
INDIVIDUALISM · public responsibility
LONG-TERM ORIENTATION · speed vs durability
SILENCE ≠
CONSENT
Country scores describe group tendencies. Direct observation must test whether they fit this team.
Notes: This message captures the central communication problem: "Why was the integration not completed?" Hall distinguishes low-context communication, where meaning is stated explicitly, from high-context communication, where relationships, status and surrounding cues carry more meaning. A low-context sender may intend a precise request for facts. A high-context recipient may infer public blame from the wording, audience and hierarchy. Hofstede adds testable hypotheses. Differences in power distance may affect willingness to challenge a leader, while individualism may affect comfort with public responsibility. Long-term orientation can also frame the recurring choice between a fast MVP and durable architecture. But national scores describe tendencies, not named people. The team must verify preferences directly. In this case, silence is mistakenly treated as consent, so an indirect technical concern remains unresolved until it becomes a blocker. Handover: Anton will diagnose how that single misunderstanding connects to wider team challenges.

## Slide 5
05
Challenges: From Task to Relationship Conflict
ANTON · 1:10
Sources: GRPI framework; Jehn et al. (1999); Abdullah (2026c)
5
G
GOALS
Fixed date
Disputed scope trade-offs
R
ROLES
Formal roles
Technical ownership diffuse
P
PROCESSES
No response, decision
or escalation rules
I
RELATIONSHIPS
Low trust
Public face threat
ESCALATION PATH
1
TASK
architecture choice
2
PROCESS
no owner or rule
3
RELATIONSHIP
public correction
PSEUDO-CONSENSUS
Different perspectives exist, but never enter the decision.
TIME-ZONE EFFECT
Specialists may be absent when live decisions are made.
Alternative explanations remain possible: technical complexity · deadline pressure · limited capacity
Notes: The GRPI model shows that the failure is systemic. At the goal level, everyone accepts the launch date but disagrees about scope and technical debt. Formal roles exist, but technical accountability is diffuse. Processes lack response deadlines, decision owners and escalation rules. Relationships are fragile because the team has no shared history. This creates pseudo-consensus: direct communicators think a decision is closed, while cautious members still have concerns. A useful task conflict about architecture then becomes a process conflict when nobody owns the decision. The public correction finally turns it into a relationship conflict. Different conflict preferences, from competing to avoiding or accommodating, strengthen this sequence. Time zones add unequal influence because specialists may be absent from live discussions. However, technical complexity, deadline pressure or limited capacity could produce the same delay, so culture is only one possible explanation. Handover: Janek will translate this diagnosis into concrete operating rules.

## Slide 6
06
Solutions: A Shared Operating Model
JANEK · 1:05
Source: G4 recommendations derived from Hall, GRPI, Belbin and conflict-management concepts
6
ASYNC DECISION PROTOCOL
01
PROPOSAL
options · evidence
owner · deadline
›
02
SITE RESPONSE
agree · concern
or question
›
03
DECISION
named owner
uses written input
›
04
LOG + REVIEW
reasoning
and review date
CORE RULE
Silence never counts as consent.
Feedback = observation + delivery impact + requested next step
RACI
clear decision rights
ROTATION
fair meeting burden
BACKUPS
specialist pairing
CHALLENGE ROLE
independent review
Conflict unresolved after 48 hours → Scrum Master mediates
Notes: The first solution is an async-first team charter. Jira tracks work, Confluence records decisions, Git supports review and Teams carries updates. Every critical proposal names its options, evidence, owner and deadline. Each site must answer "agree," "concern" or "question"; silence never counts as consent. A RACI matrix separates who performs work from who is accountable for product, process, architecture, privacy and quality. Inconvenient meeting times rotate, while specialist pairing creates backups and transfers knowledge. Because Belbin identified no Monitor Evaluator, a rotating challenge role gives one developer the legitimate task of presenting the strongest counterargument. Feedback targets an artefact rather than a person: state the observed issue, its delivery impact and the requested next step. The Scrum Master mediates unresolved conflict within 48 hours. Handover: Luca will add the leadership and trust conditions that make these rules effective.

## Slide 7
07
Solutions: Leadership and Psychological Safety
LUCA · 1:00
Sources: Aritz & Walker (2014); Edmondson (1999); Abdullah (2026c–d)
7
01
DIRECTIVE PO
Backlog order
Release scope
Urgent compliance
02
COOPERATIVE SM
Planning
Retrospectives
Input from every site
03
TRANSFORMATIONAL
Shared purpose
Individual development
Responsible global product
RESULT
Speed
+
Participation
PSYCHOLOGICAL SAFETY
Challenge ideas and report blockers without humiliation.
Safety does not lower standards; predictable reactions make interpersonal risk possible.
DOCUMENTS
coordination · decisions · reviews
VIDEO
conflict repair · relationships · pair calls
Notes: One leadership style cannot fit every situation. The Product Owner should be directive when deciding backlog order, release scope and urgent compliance questions. The Scrum Master should use cooperative leadership in planning and retrospectives, deliberately collecting input from every site. Both should use transformational leadership to connect daily tasks with a shared purpose: a stable and responsible global product. This division preserves decision speed without excluding technical evidence. It also supports psychological safety, which Edmondson defines as a shared belief that interpersonal risk-taking is safe. Safety does not lower standards; it allows members to report blockers and challenge proposals without humiliation. Leaders must respond predictably and visibly follow up. Documents support coordination, but video and rotating pair calls remain necessary for conflict repair and relationship building. Handover: Anton will separate the one observed result from the outcomes we expect after these changes.

## Slide 8
08
Outcome and Evaluation
ANTON · 0:55
Source: G4 case data and proposed Sprint 5 evaluation plan
8
OBSERVED
M1 delayed
Unresolved wearable dependency
Corrective decision in Sprint 2 retrospective
›
FORECAST · SPRINT 5
Earlier signals
Clearer ownership
Earlier risk reporting
Fewer reopened decisions
›
EXPECTED · SPRINT 11
Stable release
Smaller scope
Wearable quality and privacy protected
SPRINT 5 INDICATORS
≥ 90%
Major decisions include input from all four sites
< 10%
Decisions reopened because context was missing
100%
Known critical risks recorded before implementation
+ 0.5
Increase in psychological-safety pulse
Improvement would support the intervention, but would not prove culture caused the original delay.
Notes: We must distinguish evidence from expectation. The only observed project result is the delayed Milestone 1 and the corrective decision in the Sprint 2 retrospective. The later outcome is a forecast. By Sprint 5, the team expects clearer ownership, earlier risk reporting and fewer reopened decisions. It will test this through the decision log, risk timestamps, Definition-of-Done results and an anonymous psychological-safety pulse. The longer-term forecast is a reduced but stable release in Sprint 11, possibly with fewer social features to protect wearable quality and privacy. Improved numbers would still not prove that culture caused the original problem; easier backlog items, growing familiarity or scope reduction could also explain them. Handover: Janek closes with the lessons and our critical reflection.

## Slide 9
09
Lessons Learned and Reflection
JANEK · 1:00
Source: G4 reflection; Stahl et al. (2010)
9
01
VERIFY MEANING
Separate intention from effect.
02
STAFF FOR FIT
Balance roles, backups and time zones.
03
DESIGN TRUST
Tools coordinate work; people create trust.
04
MAKE DIFFERENCE VISIBLE
Diversity helps only when perspectives enter decisions.
CRITICAL REFLECTION
Lenses,
not labels.
Test cultural models against behaviour and alternative explanations:
product complexity
resource pressure
growing familiarity
Explicit collaboration rules turn cultural difference from a delivery risk into a source of better decisions.
Notes: We take four lessons from the case. First, intention and effect are different: directness can protect delivery and still damage trust, while politeness can preserve a relationship and still hide a blocker. Meaning must be confirmed. Second, project managers should staff global teams for role balance, specialist backups, language confidence and time-zone coverage, not availability alone. Third, digital tools can document work but cannot create trust; relationship time must be designed deliberately. Fourth, diversity improves performance only when different perspectives enter the decision. This is consistent with research showing that its benefits depend on team processes. Our models are therefore lenses, not labels. Behavioural data must test them against alternative explanations such as product complexity or resource pressure. The key takeaway is simple: explicit collaboration rules turn cultural difference from a delivery risk into a source of better decisions.

## Slide 10
10
References
Full citations are available in Cultural-Report-G4.md
10
ACADEMIC SOURCES
01
Abdullah, L. (2026). IKHT Lecture Notes 02, 04, 05 and 06.
02
Aritz, J., & Walker, R. C. (2014). Leadership styles in multicultural groups.
03
Belbin, R. M. (2010). Team Roles at Work.
04
Edmondson, A. C. (1999). Psychological safety and learning behavior in work teams.
05
Hall, E. T. (1976). Beyond Culture.
06
Hofstede, G., Hofstede, G. J., & Minkov, M. (2010). Cultures and Organizations.
07
Jehn, K. A., Northcraft, G. B., & Neale, M. A. (1999). Diversity, conflict and performance.
08
Minkov, M., & Kaasa, A. (2021). A test of Hofstede's model of culture.
09
Stahl, G. K., et al. (2010). Effects of cultural diversity in teams.
10
Tuckman, B. W. (1965). Developmental sequence in small groups.
PHOTO SOURCES
Unsplash images: photo-1521737711867-e3b97375f902 and photo-1571019613454-1cb2f99b2d8b